## Moritz
Account | Designated Heat | Issue - Description | Tickets Opened | Individual Item Resolution Date | Comments | Issue Resolution Goal
Moritz | 2011-11-10 | Need Google Ad Words code properly set up. Currently working with a May Hopper in support who has been working with our outside company Gameday the last couple of days and has been very helpful. (This was sent to Vin in May..... promised to be implemented by Aug 2nd. It is now in there and tracking, but not correctly.) |  |  | Checking on this | 2011-11-30
|  | Inventory on the bottom of the Gallery pages, promised to be done right after we went live and still not done |  |  | Checking on this
|  | Vin decoder allows you to enter an improper VIN |  |  | Garbage in = Garbage out, not much we can do about that one.
|  | Motosnap misplacing email |  |  | Need more information to troubleshoot. We're supposed to work on this one during our next call.
|  | Have to choose customer when we desk deal, when salesman has already entered the customer info. |  |  | Push Issues….already covered them in Webex. Issue resolved by training them on how to push deals to the DMS.
|  | Need a page we can put our newspaper ads. This was requested months ago, but I did not press the issue because we stopped using newspaper ads, but since we are back at it, we need it. |  |  | Need a better description of what needs to be done here. Will work on this during our next call.
|  | Issues when our salespeople are selling multiple cars to one customer |  |  | Need a better description of what needs to be done here. Will work on this during our next call.
|  | Need 301 redirecets--this was promised to be implemented by Sept 2nd, still not done. |  |  | This should be done via Website support. Check status and discuss on our next call.
|  | Finalized deal in Reynolds will never match the infromation in Vin because once the info in Reynolds is changed it does not update in Vin. |  |  | Based on our last discussion, they were going to get me some examples of this. We will talk about this more on our next call.
|  | Cannot copy and paste VIN from Silverlight. |  |  | Valid complaint, but there is nothing we can do to fix it.

## Dellenbach
Account | Designated Heat | Issue - Description | Tickets Opened | Status | Comments | Resolution Goal
Dellenbach | 2011-11-10

## Grubbs
Account | Designated Heat | Issue - Description | Tickets Opened | Status | Comments | Resolution Goal
Grubbs | 2011-11-10 |  |  |  |  | 2011-11-22

## Bonham
Account | Designated Heat | Issue - Description | Tickets Opened | Status | Comments | Resolution Goal
Bonham | 2011-11-10 |  |  |  |  | 2011-11-22

## Dealer 1
Account | Designated Heat | Issue - Description | Tickets Opened | Status | Comments | Resolution Goal

## Dealer 2
Account | Designated Heat | Issue - Description | Tickets Opened | Status | Comments | Resolution Goal